## Dashboard
Agency Project Profitability Dashboard
Executive commercial view ¦ 2026 portfolio ¦ USD
REVENUE |  | DELIVERY COST |  | GROSS PROFIT |  | GROSS MARGIN |  | BILLABLE UTIL. |  | AT-RISK PROJECTS
1431800 |  | 793728.48 |  | 638071.52 |  | 44.56% |  | 83.51% |  | 9
Project risk queue | [6 empty] | Client profitability
Project | Client | Margin | Hours Var | Cost Var | Risk |  | Client | Revenue | Gross Profit | Margin
P019 | Atlas Property | 12.28% | -1 | 3667.48 | Critical |  | Northstar Retail | 249800 | 125821.79 | 50.37%
P022 | BrightPath Learning | 36.23% | 114 | 13721.84 | Critical |  | Harbor Legal | 201200 | 90250.5 | 44.86%
P008 | PeakFit Clubs | 39.35% | 160 | 5418.09 | Critical |  | Orbit SaaS | 180600 | 82004.24 | 45.41%
P015 | Harbor Legal | 40.12% | 89 | 4905.02 | Critical |  | BrightPath Learning | 163500 | 70292.55 | 42.99%
P001 | Northstar Retail | 43.43% | 139 | 9363.22 | Critical |  | Lumen Health | 142100 | 68989.4 | 48.55%
P016 | PeakFit Clubs | 25.97% | 36 | 11303.01 | Watch |  | Cedar Finance | 166600 | 68844.58 | 41.32%
[7 empty] | PeakFit Clubs | 176900 | 67669.6 | 38.25%
[7 empty] | Atlas Property | 151100 | 64198.86 | 42.49%
Gross profit by project type
Project Type | Gross Profit | [5 empty] | Management actions • Escalate Critical projects and reforecast remaining work. • Review scope and change orders where hours exceed budget. • Protect high-margin client relationships. • Investigate non-billable time by role before staffing the next cycle.
Dashboard | 142151.93
Website | 141493.32
Campaign | 150860.86
Automation | 122573.93
Analytics Retainer | 80991.48

## Project Profitability
Project Profitability
Budget, actual delivery cost, margin, variance, and risk by engagement
Project ID | Client ID | Client | Type | Start | End | Status | Budget Hours | Revenue | Budget Cost | Rate | Actual Hours | Labor Cost | Vendor Cost | Actual Cost | Gross Profit | Margin | Hours Var | Hours Var % | Cost Var | Cost Var % | Risk
P001 | C01 | Northstar Retail | Dashboard | 2026-01-01 | 2026-03-29 | Completed | 496 | 100700 | 47600 | 181 | 635 | 50125 | 6838.22 | 56963.22 | 43736.78 | 43.43% | 139 | 28.02% | 9363.22 | 19.67% | Critical
P002 | C02 | Lumen Health | Website | 2026-01-06 | 2026-05-03 | Completed | 288 | 50100 | 28400 | 190 | 260 | 20500 | 2990.88 | 23490.88 | 26609.12 | 53.11% | -28 | -9.722% | -4909.12 | -17.29% | Healthy
P003 | C03 | Atlas Property | Campaign | 2026-01-11 | 2026-04-16 | Completed | 302 | 52700 | 30200 | 154 | 266 | 21234 | 1677.57 | 22911.57 | 29788.43 | 56.52% | -36 | -11.92% | -7288.43 | -24.13% | Healthy
P004 | C04 | Orbit SaaS | Automation | 2026-01-16 | 2026-04-26 | Completed | 532 | 104900 | 47100 | 194 | 526 | 40748 | 7808.13 | 48556.13 | 56343.87 | 53.71% | -6 | -1.128% | 1456.13 | 3.092% | Healthy
P005 | C05 | Cedar Finance | Analytics Retainer | 2026-02-01 | 2026-04-08 | Completed | 181 | 31400 | 17300 | 150 | 186 | 14772 | 3130.29 | 17902.29 | 13497.71 | 42.99% | 5 | 2.762% | 602.29 | 3.481% | Healthy
P006 | C06 | BrightPath Learning | Dashboard | 2026-02-06 | 2026-06-04 | Completed | 305 | 51500 | 30900 | 150 | 342 | 26324 | 1018.75 | 27342.75 | 24157.25 | 46.91% | 37 | 12.13% | -3557.25 | -11.51% | Watch
P007 | C07 | Harbor Legal | Website | 2026-02-11 | 2026-04-19 | Completed | 463 | 57100 | 38300 | 138 | 426 | 32407 | 3340.06 | 35747.06 | 21352.94 | 37.4% | -37 | -7.991% | -2552.94 | -6.666% | Healthy
P008 | C08 | PeakFit Clubs | Campaign | 2026-02-16 | 2026-05-21 | Completed | 570 | 94500 | 51900 | 159 | 730 | 56371 | 947.09 | 57318.09 | 37181.91 | 39.35% | 160 | 28.07% | 5418.09 | 10.44% | Critical
P009 | C01 | Northstar Retail | Automation | 2026-03-01 | 2026-05-22 | Completed | 348 | 56400 | 29900 | 157 | 343 | 27075 | 2175.3 | 29250.3 | 27149.7 | 48.14% | -5 | -1.437% | -649.7 | -2.173% | Healthy
P010 | C02 | Lumen Health | Analytics Retainer | 2026-03-06 | 2026-06-20 | Completed | 289 | 62100 | 30200 | 186 | 298 | 24722 | 9421.79 | 34143.79 | 27956.21 | 45.02% | 9 | 3.114% | 3943.79 | 13.06% | Healthy
P011 | C03 | Atlas Property | Dashboard | 2026-03-11 | 2026-05-12 | Completed | 392 | 67200 | 37500 | 192 | 439 | 35184 | 1438.09 | 36622.09 | 30577.91 | 45.5% | 47 | 11.99% | -877.91 | -2.341% | Watch
P012 | C04 | Orbit SaaS | Website | 2026-03-16 | 2026-06-06 | Completed | 176 | 29200 | 16400 | 164 | 166 | 13110 | 5572.21 | 18682.21 | 10517.79 | 36.02% | -10 | -5.682% | 2282.21 | 13.92% | Healthy
P013 | C05 | Cedar Finance | Campaign | 2026-04-01 | 2026-07-12 | Completed | 310 | 55300 | 31500 | 182 | 267 | 21386 | 8950.13 | 30336.13 | 24963.87 | 45.14% | -43 | -13.87% | -1163.87 | -3.695% | Healthy
P014 | C06 | BrightPath Learning | Automation | 2026-04-06 | 2026-07-13 | Completed | 179 | 34500 | 16900 | 193 | 162 | 12695 | 3747.86 | 16442.86 | 18057.14 | 52.34% | -17 | -9.497% | -457.14 | -2.705% | Healthy
P015 | C07 | Harbor Legal | Analytics Retainer | 2026-04-11 | 2026-06-14 | Completed | 317 | 60800 | 31500 | 179 | 406 | 31321 | 5084.02 | 36405.02 | 24394.98 | 40.12% | 89 | 28.08% | 4905.02 | 15.57% | Critical
P016 | C08 | PeakFit Clubs | Dashboard | 2026-04-16 | 2026-06-14 | At Risk | 302 | 51200 | 26600 | 164 | 338 | 27083 | 10820.01 | 37903.01 | 13296.99 | 25.97% | 36 | 11.92% | 11303.01 | 42.49% | Watch
P017 | C01 | Northstar Retail | Website | 2026-05-01 | 2026-06-30 | Active | 557 | 92700 | 54100 | 187 | 467 | 36667 | 1097.69 | 37764.69 | 54935.31 | 59.26% | -90 | -16.16% | -16335.31 | -30.19% | Healthy
P018 | C02 | Lumen Health | Campaign | 2026-05-06 | 2026-07-23 | At Risk | 196 | 29900 | 18300 | 147 | 169 | 13456 | 2019.93 | 15475.93 | 14424.07 | 48.24% | -27 | -13.78% | -2824.07 | -15.43% | Healthy
P019 | C03 | Atlas Property | Automation | 2026-05-11 | 2026-08-05 | Active | 242 | 31200 | 23700 | 140 | 241 | 19104 | 8263.48 | 27367.48 | 3832.52 | 12.28% | -1 | -0.4132% | 3667.48 | 15.47% | Critical
P020 | C04 | Orbit SaaS | Analytics Retainer | 2026-05-16 | 2026-07-03 | At Risk | 335 | 46500 | 29500 | 149 | 336 | 26918 | 4439.42 | 31357.42 | 15142.58 | 32.56% | 1 | 0.2985% | 1857.42 | 6.296% | Healthy
P021 | C05 | Cedar Finance | Dashboard | 2026-06-01 | 2026-07-31 | Active | 525 | 79900 | 45100 | 162 | 588 | 45683 | 3834 | 49517 | 30383 | 38.03% | 63 | 12% | 4417 | 9.794% | Watch
P022 | C06 | BrightPath Learning | Website | 2026-06-06 | 2026-09-06 | At Risk | 408 | 77500 | 35700 | 169 | 522 | 41383 | 8038.84 | 49421.84 | 28078.16 | 36.23% | 114 | 27.94% | 13721.84 | 38.44% | Critical
P023 | C07 | Harbor Legal | Campaign | 2026-06-11 | 2026-08-27 | Active | 539 | 83300 | 47500 | 159 | 476 | 37363 | 1434.42 | 38797.42 | 44502.58 | 53.42% | -63 | -11.69% | -8702.58 | -18.32% | Healthy
P024 | C08 | PeakFit Clubs | Automation | 2026-06-16 | 2026-10-03 | At Risk | 180 | 31200 | 17100 | 176 | 149 | 11649 | 2360.3 | 14009.3 | 17190.7 | 55.1% | -31 | -17.22% | -3090.7 | -18.07% | Healthy

## Time Entries
Time Entries
Source-level hours and labor cost; billable hours support utilization
Time ID | Project ID | Staff ID | Staff | Role | Date | Hours | Labor Cost | Billable Hours
T00001 | P001 | S01 | Maya Chen | Strategy | 2026-01-04 | 44 | 4180 | 44
T00002 | P001 | S02 | Elias Ward | Design | 2026-02-11 | 41 | 2952 | 41
T00003 | P001 | S03 | Nora Patel | Analytics | 2026-02-09 | 34 | 2788 | 34
T00004 | P001 | S04 | Owen Brooks | Development | 2026-02-04 | 37 | 3256 | 37
T00005 | P001 | S05 | Sara Lin | Project Management | 2026-03-22 | 30 | 2100 | 30
T00006 | P001 | S06 | Leo Martin | Development | 2026-02-14 | 40 | 3680 | 40
T00007 | P001 | S07 | Ava Stone | Content | 2026-01-04 | 25 | 1450 | 25
T00008 | P001 | S08 | Theo King | Analytics | 2026-02-24 | 26 | 2028 | 26
T00009 | P001 | S09 | Emma Hayes | Design | 2026-01-03 | 28 | 1904 | 28
T00010 | P001 | S10 | Noah Reed | Strategy | 2026-03-11 | 29 | 2610 | 0
T00011 | P001 | S01 | Maya Chen | Strategy | 2026-03-10 | 29 | 2755 | 29
T00012 | P001 | S02 | Elias Ward | Design | 2026-02-09 | 35 | 2520 | 0
T00013 | P001 | S03 | Nora Patel | Analytics | 2026-01-04 | 46 | 3772 | 46
T00014 | P001 | S04 | Owen Brooks | Development | 2026-02-03 | 50 | 4400 | 50
T00015 | P001 | S05 | Sara Lin | Project Management | 2026-01-04 | 33 | 2310 | 33
T00016 | P001 | S06 | Leo Martin | Development | 2026-01-30 | 34 | 3128 | 34
T00017 | P001 | S07 | Ava Stone | Content | 2026-02-22 | 74 | 4292 | 74
T00018 | P002 | S02 | Elias Ward | Design | 2026-04-11 | 13 | 936 | 13
T00019 | P002 | S03 | Nora Patel | Analytics | 2026-01-13 | 12 | 984 | 12
T00020 | P002 | S04 | Owen Brooks | Development | 2026-03-15 | 13 | 1144 | 0
T00021 | P002 | S05 | Sara Lin | Project Management | 2026-02-21 | 9 | 630 | 9
T00022 | P002 | S06 | Leo Martin | Development | 2026-01-25 | 12 | 1104 | 12
T00023 | P002 | S07 | Ava Stone | Content | 2026-04-29 | 17 | 986 | 17
T00024 | P002 | S08 | Theo King | Analytics | 2026-04-08 | 13 | 1014 | 13
T00025 | P002 | S09 | Emma Hayes | Design | 2026-04-26 | 11 | 748 | 11
T00026 | P002 | S10 | Noah Reed | Strategy | 2026-01-26 | 16 | 1440 | 16
T00027 | P002 | S01 | Maya Chen | Strategy | 2026-02-09 | 16 | 1520 | 0
T00028 | P002 | S02 | Elias Ward | Design | 2026-04-26 | 12 | 864 | 12
T00029 | P002 | S03 | Nora Patel | Analytics | 2026-03-02 | 11 | 902 | 11
T00030 | P002 | S04 | Owen Brooks | Development | 2026-02-24 | 11 | 968 | 11
T00031 | P002 | S05 | Sara Lin | Project Management | 2026-04-30 | 17 | 1190 | 17
T00032 | P002 | S06 | Leo Martin | Development | 2026-04-18 | 14 | 1288 | 14
T00033 | P002 | S07 | Ava Stone | Content | 2026-02-09 | 16 | 928 | 16
T00034 | P002 | S08 | Theo King | Analytics | 2026-03-06 | 9 | 702 | 9
T00035 | P002 | S09 | Emma Hayes | Design | 2026-03-07 | 14 | 952 | 14
T00036 | P002 | S10 | Noah Reed | Strategy | 2026-02-18 | 16 | 1440 | 16
T00037 | P002 | S01 | Maya Chen | Strategy | 2026-03-01 | 8 | 760 | 8
T00038 | P003 | S03 | Nora Patel | Analytics | 2026-01-17 | 26 | 2132 | 26
T00039 | P003 | S04 | Owen Brooks | Development | 2026-02-27 | 24 | 2112 | 0
T00040 | P003 | S05 | Sara Lin | Project Management | 2026-02-23 | 20 | 1400 | 20
T00041 | P003 | S06 | Leo Martin | Development | 2026-04-11 | 22 | 2024 | 22
T00042 | P003 | S07 | Ava Stone | Content | 2026-02-03 | 28 | 1624 | 28
T00043 | P003 | S08 | Theo King | Analytics | 2026-03-27 | 19 | 1482 | 19
T00044 | P003 | S09 | Emma Hayes | Design | 2026-02-28 | 26 | 1768 | 0
T00045 | P003 | S10 | Noah Reed | Strategy | 2026-04-15 | 21 | 1890 | 0
T00046 | P003 | S01 | Maya Chen | Strategy | 2026-02-12 | 28 | 2660 | 28
T00047 | P003 | S02 | Elias Ward | Design | 2026-01-25 | 17 | 1224 | 17
T00048 | P003 | S03 | Nora Patel | Analytics | 2026-02-08 | 27 | 2214 | 27
T00049 | P003 | S04 | Owen Brooks | Development | 2026-03-29 | 8 | 704 | 0
T00050 | P004 | S04 | Owen Brooks | Development | 2026-04-12 | 25 | 2200 | 25
T00051 | P004 | S05 | Sara Lin | Project Management | 2026-01-29 | 32 | 2240 | 32
T00052 | P004 | S06 | Leo Martin | Development | 2026-04-09 | 22 | 2024 | 22
T00053 | P004 | S07 | Ava Stone | Content | 2026-04-15 | 35 | 2030 | 35
T00054 | P004 | S08 | Theo King | Analytics | 2026-04-22 | 25 | 1950 | 25
T00055 | P004 | S09 | Emma Hayes | Design | 2026-03-07 | 33 | 2244 | 33
T00056 | P004 | S10 | Noah Reed | Strategy | 2026-02-25 | 39 | 3510 | 39
T00057 | P004 | S01 | Maya Chen | Strategy | 2026-04-19 | 28 | 2660 | 0
T00058 | P004 | S02 | Elias Ward | Design | 2026-02-22 | 36 | 2592 | 36
T00059 | P004 | S03 | Nora Patel | Analytics | 2026-01-20 | 36 | 2952 | 36
T00060 | P004 | S04 | Owen Brooks | Development | 2026-04-02 | 41 | 3608 | 41
T00061 | P004 | S05 | Sara Lin | Project Management | 2026-01-23 | 21 | 1470 | 21
T00062 | P004 | S06 | Leo Martin | Development | 2026-04-11 | 22 | 2024 | 22
T00063 | P004 | S07 | Ava Stone | Content | 2026-03-29 | 42 | 2436 | 42
T00064 | P004 | S08 | Theo King | Analytics | 2026-01-28 | 36 | 2808 | 36
T00065 | P004 | S09 | Emma Hayes | Design | 2026-01-16 | 35 | 2380 | 35
T00066 | P004 | S10 | Noah Reed | Strategy | 2026-02-07 | 18 | 1620 | 18
T00067 | P005 | S05 | Sara Lin | Project Management | 2026-02-10 | 17 | 1190 | 17
T00068 | P005 | S06 | Leo Martin | Development | 2026-04-04 | 12 | 1104 | 12
T00069 | P005 | S07 | Ava Stone | Content | 2026-03-02 | 11 | 638 | 11
T00070 | P005 | S08 | Theo King | Analytics | 2026-04-02 | 20 | 1560 | 0
T00071 | P005 | S09 | Emma Hayes | Design | 2026-04-01 | 18 | 1224 | 0
T00072 | P005 | S10 | Noah Reed | Strategy | 2026-03-13 | 13 | 1170 | 0
T00073 | P005 | S01 | Maya Chen | Strategy | 2026-03-02 | 16 | 1520 | 16
T00074 | P005 | S02 | Elias Ward | Design | 2026-03-24 | 14 | 1008 | 14
T00075 | P005 | S03 | Nora Patel | Analytics | 2026-02-16 | 11 | 902 | 11
T00076 | P005 | S04 | Owen Brooks | Development | 2026-02-24 | 18 | 1584 | 0
T00077 | P005 | S05 | Sara Lin | Project Management | 2026-03-03 | 20 | 1400 | 20
T00078 | P005 | S06 | Leo Martin | Development | 2026-02-27 | 16 | 1472 | 16
T00079 | P006 | S06 | Leo Martin | Development | 2026-03-15 | 29 | 2668 | 0
T00080 | P006 | S07 | Ava Stone | Content | 2026-05-19 | 28 | 1624 | 28
T00081 | P006 | S08 | Theo King | Analytics | 2026-02-22 | 23 | 1794 | 0
T00082 | P006 | S09 | Emma Hayes | Design | 2026-05-01 | 23 | 1564 | 23
T00083 | P006 | S10 | Noah Reed | Strategy | 2026-03-09 | 28 | 2520 | 28
T00084 | P006 | S01 | Maya Chen | Strategy | 2026-04-24 | 16 | 1520 | 16
T00085 | P006 | S02 | Elias Ward | Design | 2026-04-19 | 18 | 1296 | 18
T00086 | P006 | S03 | Nora Patel | Analytics | 2026-04-19 | 24 | 1968 | 24
T00087 | P006 | S04 | Owen Brooks | Development | 2026-03-10 | 17 | 1496 | 17
T00088 | P006 | S05 | Sara Lin | Project Management | 2026-02-23 | 29 | 2030 | 29
T00089 | P006 | S06 | Leo Martin | Development | 2026-02-06 | 22 | 2024 | 22
T00090 | P006 | S07 | Ava Stone | Content | 2026-03-18 | 19 | 1102 | 19
T00091 | P006 | S08 | Theo King | Analytics | 2026-03-10 | 23 | 1794 | 23
T00092 | P006 | S09 | Emma Hayes | Design | 2026-03-30 | 43 | 2924 | 0
T00093 | P007 | S07 | Ava Stone | Content | 2026-02-20 | 33 | 1914 | 33
T00094 | P007 | S08 | Theo King | Analytics | 2026-03-06 | 22 | 1716 | 22
T00095 | P007 | S09 | Emma Hayes | Design | 2026-04-08 | 25 | 1700 | 0
T00096 | P007 | S10 | Noah Reed | Strategy | 2026-02-15 | 41 | 3690 | 41
T00097 | P007 | S01 | Maya Chen | Strategy | 2026-02-16 | 37 | 3515 | 37
T00098 | P007 | S02 | Elias Ward | Design | 2026-03-26 | 31 | 2232 | 31
T00099 | P007 | S03 | Nora Patel | Analytics | 2026-03-05 | 24 | 1968 | 24
T00100 | P007 | S04 | Owen Brooks | Development | 2026-02-11 | 35 | 3080 | 35
T00101 | P007 | S05 | Sara Lin | Project Management | 2026-03-07 | 30 | 2100 | 30
T00102 | P007 | S06 | Leo Martin | Development | 2026-03-10 | 22 | 2024 | 22
T00103 | P007 | S07 | Ava Stone | Content | 2026-03-12 | 36 | 2088 | 36
T00104 | P007 | S08 | Theo King | Analytics | 2026-03-09 | 26 | 2028 | 26
T00105 | P007 | S09 | Emma Hayes | Design | 2026-04-04 | 64 | 4352 | 64
T00106 | P008 | S08 | Theo King | Analytics | 2026-05-18 | 28 | 2184 | 28
T00107 | P008 | S09 | Emma Hayes | Design | 2026-04-27 | 27 | 1836 | 27
T00108 | P008 | S10 | Noah Reed | Strategy | 2026-04-14 | 36 | 3240 | 36
T00109 | P008 | S01 | Maya Chen | Strategy | 2026-03-28 | 31 | 2945 | 31
T00110 | P008 | S02 | Elias Ward | Design | 2026-03-24 | 26 | 1872 | 26
T00111 | P008 | S03 | Nora Patel | Analytics | 2026-03-03 | 35 | 2870 | 35
T00112 | P008 | S04 | Owen Brooks | Development | 2026-04-13 | 29 | 2552 | 29
T00113 | P008 | S05 | Sara Lin | Project Management | 2026-03-07 | 44 | 3080 | 44
T00114 | P008 | S06 | Leo Martin | Development | 2026-04-16 | 35 | 3220 | 35
T00115 | P008 | S07 | Ava Stone | Content | 2026-03-16 | 39 | 2262 | 39
T00116 | P008 | S08 | Theo King | Analytics | 2026-04-30 | 25 | 1950 | 25
T00117 | P008 | S09 | Emma Hayes | Design | 2026-05-03 | 37 | 2516 | 37
T00118 | P008 | S10 | Noah Reed | Strategy | 2026-03-28 | 24 | 2160 | 24
T00119 | P008 | S01 | Maya Chen | Strategy | 2026-03-20 | 32 | 3040 | 32
T00120 | P008 | S02 | Elias Ward | Design | 2026-04-02 | 44 | 3168 | 44
T00121 | P008 | S03 | Nora Patel | Analytics | 2026-05-02 | 44 | 3608 | 44
T00122 | P008 | S04 | Owen Brooks | Development | 2026-04-12 | 41 | 3608 | 41
T00123 | P008 | S05 | Sara Lin | Project Management | 2026-03-03 | 39 | 2730 | 39
T00124 | P008 | S06 | Leo Martin | Development | 2026-03-06 | 27 | 2484 | 27
T00125 | P008 | S07 | Ava Stone | Content | 2026-05-15 | 87 | 5046 | 87
T00126 | P009 | S09 | Emma Hayes | Design | 2026-04-03 | 15 | 1020 | 15
T00127 | P009 | S10 | Noah Reed | Strategy | 2026-03-12 | 20 | 1800 | 20
T00128 | P009 | S01 | Maya Chen | Strategy | 2026-03-07 | 20 | 1900 | 20
T00129 | P009 | S02 | Elias Ward | Design | 2026-03-29 | 12 | 864 | 0
T00130 | P009 | S03 | Nora Patel | Analytics | 2026-03-26 | 11 | 902 | 11
T00131 | P009 | S04 | Owen Brooks | Development | 2026-04-09 | 14 | 1232 | 0
T00132 | P009 | S05 | Sara Lin | Project Management | 2026-05-05 | 11 | 770 | 11
T00133 | P009 | S06 | Leo Martin | Development | 2026-04-24 | 17 | 1564 | 17
T00134 | P009 | S07 | Ava Stone | Content | 2026-03-06 | 12 | 696 | 12
T00135 | P009 | S08 | Theo King | Analytics | 2026-03-17 | 19 | 1482 | 19
T00136 | P009 | S09 | Emma Hayes | Design | 2026-04-15 | 19 | 1292 | 19
T00137 | P009 | S10 | Noah Reed | Strategy | 2026-03-03 | 12 | 1080 | 0
T00138 | P009 | S01 | Maya Chen | Strategy | 2026-04-11 | 17 | 1615 | 17
T00139 | P009 | S02 | Elias Ward | Design | 2026-03-12 | 14 | 1008 | 0
T00140 | P009 | S03 | Nora Patel | Analytics | 2026-05-18 | 14 | 1148 | 14
T00141 | P009 | S04 | Owen Brooks | Development | 2026-04-16 | 17 | 1496 | 17
T00142 | P009 | S05 | Sara Lin | Project Management | 2026-03-09 | 14 | 980 | 14
T00143 | P009 | S06 | Leo Martin | Development | 2026-04-10 | 19 | 1748 | 19
T00144 | P009 | S07 | Ava Stone | Content | 2026-04-06 | 17 | 986 | 0
T00145 | P009 | S08 | Theo King | Analytics | 2026-05-01 | 16 | 1248 | 16
T00146 | P009 | S09 | Emma Hayes | Design | 2026-04-21 | 33 | 2244 | 0
T00147 | P010 | S10 | Noah Reed | Strategy | 2026-03-20 | 33 | 2970 | 33
T00148 | P010 | S01 | Maya Chen | Strategy | 2026-04-11 | 22 | 2090 | 0
T00149 | P010 | S02 | Elias Ward | Design | 2026-04-28 | 19 | 1368 | 19
T00150 | P010 | S03 | Nora Patel | Analytics | 2026-05-24 | 18 | 1476 | 18
T00151 | P010 | S04 | Owen Brooks | Development | 2026-06-01 | 30 | 2640 | 30
T00152 | P010 | S05 | Sara Lin | Project Management | 2026-05-17 | 17 | 1190 | 17
T00153 | P010 | S06 | Leo Martin | Development | 2026-05-25 | 24 | 2208 | 24
T00154 | P010 | S07 | Ava Stone | Content | 2026-05-01 | 23 | 1334 | 23
T00155 | P010 | S08 | Theo King | Analytics | 2026-04-08 | 33 | 2574 | 33
T00156 | P010 | S09 | Emma Hayes | Design | 2026-06-19 | 19 | 1292 | 0
T00157 | P010 | S10 | Noah Reed | Strategy | 2026-03-24 | 24 | 2160 | 24
T00158 | P010 | S01 | Maya Chen | Strategy | 2026-03-27 | 36 | 3420 | 36
T00159 | P011 | S01 | Maya Chen | Strategy | 2026-04-23 | 22 | 2090 | 22
T00160 | P011 | S02 | Elias Ward | Design | 2026-03-30 | 29 | 2088 | 0
T00161 | P011 | S03 | Nora Patel | Analytics | 2026-04-24 | 34 | 2788 | 0
T00162 | P011 | S04 | Owen Brooks | Development | 2026-04-29 | 20 | 1760 | 20
T00163 | P011 | S05 | Sara Lin | Project Management | 2026-04-11 | 19 | 1330 | 19
T00164 | P011 | S06 | Leo Martin | Development | 2026-04-10 | 22 | 2024 | 22
T00165 | P011 | S07 | Ava Stone | Content | 2026-04-23 | 29 | 1682 | 29
T00166 | P011 | S08 | Theo King | Analytics | 2026-03-26 | 33 | 2574 | 33
T00167 | P011 | S09 | Emma Hayes | Design | 2026-05-05 | 27 | 1836 | 0
T00168 | P011 | S10 | Noah Reed | Strategy | 2026-03-30 | 28 | 2520 | 28
T00169 | P011 | S01 | Maya Chen | Strategy | 2026-03-20 | 32 | 3040 | 32
T00170 | P011 | S02 | Elias Ward | Design | 2026-04-25 | 23 | 1656 | 23
T00171 | P011 | S03 | Nora Patel | Analytics | 2026-04-10 | 30 | 2460 | 30
T00172 | P011 | S04 | Owen Brooks | Development | 2026-04-15 | 23 | 2024 | 23
T00173 | P011 | S05 | Sara Lin | Project Management | 2026-04-19 | 29 | 2030 | 29
T00174 | P011 | S06 | Leo Martin | Development | 2026-04-16 | 30 | 2760 | 30
T00175 | P011 | S07 | Ava Stone | Content | 2026-04-13 | 9 | 522 | 0
T00176 | P012 | S02 | Elias Ward | Design | 2026-06-05 | 14 | 1008 | 14
T00177 | P012 | S03 | Nora Patel | Analytics | 2026-03-20 | 9 | 738 | 0
T00178 | P012 | S04 | Owen Brooks | Development | 2026-05-19 | 14 | 1232 | 14
T00179 | P012 | S05 | Sara Lin | Project Management | 2026-03-23 | 12 | 840 | 12
T00180 | P012 | S06 | Leo Martin | Development | 2026-04-19 | 10 | 920 | 10
T00181 | P012 | S07 | Ava Stone | Content | 2026-05-09 | 13 | 754 | 0
T00182 | P012 | S08 | Theo King | Analytics | 2026-04-15 | 14 | 1092 | 14
T00183 | P012 | S09 | Emma Hayes | Design | 2026-05-24 | 12 | 816 | 12
T00184 | P012 | S10 | Noah Reed | Strategy | 2026-04-09 | 8 | 720 | 8
T00185 | P012 | S01 | Maya Chen | Strategy | 2026-04-03 | 14 | 1330 | 14
T00186 | P012 | S02 | Elias Ward | Design | 2026-03-18 | 10 | 720 | 10
T00187 | P012 | S03 | Nora Patel | Analytics | 2026-05-28 | 14 | 1148 | 14
T00188 | P012 | S04 | Owen Brooks | Development | 2026-03-29 | 14 | 1232 | 14
T00189 | P012 | S05 | Sara Lin | Project Management | 2026-03-26 | 8 | 560 | 8
T00190 | P013 | S03 | Nora Patel | Analytics | 2026-06-04 | 16 | 1312 | 16
T00191 | P013 | S04 | Owen Brooks | Development | 2026-05-26 | 13 | 1144 | 0
T00192 | P013 | S05 | Sara Lin | Project Management | 2026-04-25 | 15 | 1050 | 15
T00193 | P013 | S06 | Leo Martin | Development | 2026-05-13 | 11 | 1012 | 11
T00194 | P013 | S07 | Ava Stone | Content | 2026-05-30 | 9 | 522 | 9
T00195 | P013 | S08 | Theo King | Analytics | 2026-05-29 | 8 | 624 | 8
T00196 | P013 | S09 | Emma Hayes | Design | 2026-04-26 | 9 | 612 | 9
T00197 | P013 | S10 | Noah Reed | Strategy | 2026-04-24 | 12 | 1080 | 12
T00198 | P013 | S01 | Maya Chen | Strategy | 2026-05-01 | 14 | 1330 | 14
T00199 | P013 | S02 | Elias Ward | Design | 2026-06-22 | 11 | 792 | 11
T00200 | P013 | S03 | Nora Patel | Analytics | 2026-06-28 | 16 | 1312 | 16
T00201 | P013 | S04 | Owen Brooks | Development | 2026-05-18 | 17 | 1496 | 17
T00202 | P013 | S05 | Sara Lin | Project Management | 2026-06-11 | 10 | 700 | 0
T00203 | P013 | S06 | Leo Martin | Development | 2026-07-08 | 17 | 1564 | 17
T00204 | P013 | S07 | Ava Stone | Content | 2026-05-20 | 13 | 754 | 13
T00205 | P013 | S08 | Theo King | Analytics | 2026-04-20 | 17 | 1326 | 0
T00206 | P013 | S09 | Emma Hayes | Design | 2026-04-09 | 13 | 884 | 13
T00207 | P013 | S10 | Noah Reed | Strategy | 2026-04-02 | 15 | 1350 | 15
T00208 | P013 | S01 | Maya Chen | Strategy | 2026-05-13 | 10 | 950 | 0
T00209 | P013 | S02 | Elias Ward | Design | 2026-06-05 | 15 | 1080 | 15
T00210 | P013 | S03 | Nora Patel | Analytics | 2026-05-19 | 6 | 492 | 6
T00211 | P014 | S04 | Owen Brooks | Development | 2026-05-31 | 11 | 968 | 11
T00212 | P014 | S05 | Sara Lin | Project Management | 2026-05-30 | 7 | 490 | 0
T00213 | P014 | S06 | Leo Martin | Development | 2026-04-06 | 7 | 644 | 7
T00214 | P014 | S07 | Ava Stone | Content | 2026-06-10 | 9 | 522 | 9
T00215 | P014 | S08 | Theo King | Analytics | 2026-06-21 | 8 | 624 | 8
T00216 | P014 | S09 | Emma Hayes | Design | 2026-05-03 | 9 | 612 | 9
T00217 | P014 | S10 | Noah Reed | Strategy | 2026-06-17 | 7 | 630 | 0
T00218 | P014 | S01 | Maya Chen | Strategy | 2026-04-20 | 6 | 570 | 6
T00219 | P014 | S02 | Elias Ward | Design | 2026-06-13 | 8 | 576 | 8
T00220 | P014 | S03 | Nora Patel | Analytics | 2026-07-04 | 10 | 820 | 10
T00221 | P014 | S04 | Owen Brooks | Development | 2026-06-04 | 7 | 616 | 7
T00222 | P014 | S05 | Sara Lin | Project Management | 2026-07-01 | 11 | 770 | 0
T00223 | P014 | S06 | Leo Martin | Development | 2026-06-23 | 6 | 552 | 6
T00224 | P014 | S07 | Ava Stone | Content | 2026-05-02 | 9 | 522 | 0
T00225 | P014 | S08 | Theo King | Analytics | 2026-05-24 | 6 | 468 | 6
T00226 | P014 | S09 | Emma Hayes | Design | 2026-05-31 | 7 | 476 | 7
T00227 | P014 | S10 | Noah Reed | Strategy | 2026-05-10 | 10 | 900 | 10
T00228 | P014 | S01 | Maya Chen | Strategy | 2026-04-13 | 9 | 855 | 0
T00229 | P014 | S02 | Elias Ward | Design | 2026-06-10 | 15 | 1080 | 15
T00230 | P015 | S05 | Sara Lin | Project Management | 2026-05-13 | 31 | 2170 | 31
T00231 | P015 | S06 | Leo Martin | Development | 2026-05-15 | 27 | 2484 | 27
T00232 | P015 | S07 | Ava Stone | Content | 2026-04-23 | 26 | 1508 | 26
T00233 | P015 | S08 | Theo King | Analytics | 2026-04-21 | 26 | 2028 | 26
T00234 | P015 | S09 | Emma Hayes | Design | 2026-05-31 | 28 | 1904 | 28
T00235 | P015 | S10 | Noah Reed | Strategy | 2026-04-28 | 22 | 1980 | 22
T00236 | P015 | S01 | Maya Chen | Strategy | 2026-05-26 | 21 | 1995 | 21
T00237 | P015 | S02 | Elias Ward | Design | 2026-04-15 | 25 | 1800 | 0
T00238 | P015 | S03 | Nora Patel | Analytics | 2026-06-03 | 31 | 2542 | 31
T00239 | P015 | S04 | Owen Brooks | Development | 2026-05-30 | 25 | 2200 | 25
T00240 | P015 | S05 | Sara Lin | Project Management | 2026-04-19 | 32 | 2240 | 0
T00241 | P015 | S06 | Leo Martin | Development | 2026-05-17 | 28 | 2576 | 28
T00242 | P015 | S07 | Ava Stone | Content | 2026-04-20 | 23 | 1334 | 23
T00243 | P015 | S08 | Theo King | Analytics | 2026-06-02 | 28 | 2184 | 0
T00244 | P015 | S09 | Emma Hayes | Design | 2026-05-28 | 27 | 1836 | 27
T00245 | P015 | S10 | Noah Reed | Strategy | 2026-06-08 | 6 | 540 | 6
T00246 | P016 | S06 | Leo Martin | Development | 2026-06-01 | 38 | 3496 | 38
T00247 | P016 | S07 | Ava Stone | Content | 2026-04-22 | 24 | 1392 | 0
T00248 | P016 | S08 | Theo King | Analytics | 2026-04-27 | 38 | 2964 | 38
T00249 | P016 | S09 | Emma Hayes | Design | 2026-05-15 | 23 | 1564 | 23
T00250 | P016 | S10 | Noah Reed | Strategy | 2026-05-05 | 27 | 2430 | 27
T00251 | P016 | S01 | Maya Chen | Strategy | 2026-05-19 | 21 | 1995 | 0
T00252 | P016 | S02 | Elias Ward | Design | 2026-05-31 | 24 | 1728 | 24
T00253 | P016 | S03 | Nora Patel | Analytics | 2026-05-04 | 22 | 1804 | 22
T00254 | P016 | S04 | Owen Brooks | Development | 2026-05-15 | 37 | 3256 | 0
T00255 | P016 | S05 | Sara Lin | Project Management | 2026-04-21 | 27 | 1890 | 27
T00256 | P016 | S06 | Leo Martin | Development | 2026-05-24 | 37 | 3404 | 0
T00257 | P016 | S07 | Ava Stone | Content | 2026-05-09 | 20 | 1160 | 20
T00258 | P017 | S07 | Ava Stone | Content | 2026-06-29 | 27 | 1566 | 27
T00259 | P017 | S08 | Theo King | Analytics | 2026-06-04 | 28 | 2184 | 28
T00260 | P017 | S09 | Emma Hayes | Design | 2026-06-28 | 36 | 2448 | 36
T00261 | P017 | S10 | Noah Reed | Strategy | 2026-05-20 | 40 | 3600 | 40
T00262 | P017 | S01 | Maya Chen | Strategy | 2026-05-08 | 31 | 2945 | 0
T00263 | P017 | S02 | Elias Ward | Design | 2026-05-23 | 25 | 1800 | 25
T00264 | P017 | S03 | Nora Patel | Analytics | 2026-05-29 | 44 | 3608 | 0
T00265 | P017 | S04 | Owen Brooks | Development | 2026-06-01 | 45 | 3960 | 45
T00266 | P017 | S05 | Sara Lin | Project Management | 2026-06-13 | 35 | 2450 | 35
T00267 | P017 | S06 | Leo Martin | Development | 2026-05-20 | 38 | 3496 | 38
T00268 | P017 | S07 | Ava Stone | Content | 2026-06-12 | 26 | 1508 | 26
T00269 | P017 | S08 | Theo King | Analytics | 2026-05-27 | 23 | 1794 | 23
T00270 | P017 | S09 | Emma Hayes | Design | 2026-05-05 | 41 | 2788 | 0
T00271 | P017 | S10 | Noah Reed | Strategy | 2026-06-08 | 28 | 2520 | 28
T00272 | P018 | S08 | Theo King | Analytics | 2026-07-15 | 9 | 702 | 9
T00273 | P018 | S09 | Emma Hayes | Design | 2026-07-17 | 10 | 680 | 10
T00274 | P018 | S10 | Noah Reed | Strategy | 2026-05-19 | 17 | 1530 | 17
T00275 | P018 | S01 | Maya Chen | Strategy | 2026-06-26 | 14 | 1330 | 14
T00276 | P018 | S02 | Elias Ward | Design | 2026-05-28 | 16 | 1152 | 16
T00277 | P018 | S03 | Nora Patel | Analytics | 2026-06-02 | 11 | 902 | 11
T00278 | P018 | S04 | Owen Brooks | Development | 2026-06-29 | 13 | 1144 | 13
T00279 | P018 | S05 | Sara Lin | Project Management | 2026-05-27 | 10 | 700 | 10
T00280 | P018 | S06 | Leo Martin | Development | 2026-05-14 | 9 | 828 | 9
T00281 | P018 | S07 | Ava Stone | Content | 2026-05-29 | 16 | 928 | 0
T00282 | P018 | S08 | Theo King | Analytics | 2026-05-09 | 15 | 1170 | 15
T00283 | P018 | S09 | Emma Hayes | Design | 2026-07-12 | 10 | 680 | 10
T00284 | P018 | S10 | Noah Reed | Strategy | 2026-06-29 | 19 | 1710 | 19
T00285 | P019 | S09 | Emma Hayes | Design | 2026-07-06 | 16 | 1088 | 16
T00286 | P019 | S10 | Noah Reed | Strategy | 2026-05-14 | 10 | 900 | 10
T00287 | P019 | S01 | Maya Chen | Strategy | 2026-06-23 | 12 | 1140 | 12
T00288 | P019 | S02 | Elias Ward | Design | 2026-07-05 | 12 | 864 | 12
T00289 | P019 | S03 | Nora Patel | Analytics | 2026-05-31 | 15 | 1230 | 15
T00290 | P019 | S04 | Owen Brooks | Development | 2026-06-24 | 11 | 968 | 11
T00291 | P019 | S05 | Sara Lin | Project Management | 2026-05-19 | 17 | 1190 | 17
T00292 | P019 | S06 | Leo Martin | Development | 2026-07-16 | 14 | 1288 | 0
T00293 | P019 | S07 | Ava Stone | Content | 2026-07-08 | 13 | 754 | 13
T00294 | P019 | S08 | Theo King | Analytics | 2026-07-12 | 18 | 1404 | 18
T00295 | P019 | S09 | Emma Hayes | Design | 2026-07-20 | 9 | 612 | 9
T00296 | P019 | S10 | Noah Reed | Strategy | 2026-06-25 | 12 | 1080 | 12
T00297 | P019 | S01 | Maya Chen | Strategy | 2026-07-01 | 10 | 950 | 10
T00298 | P019 | S02 | Elias Ward | Design | 2026-07-19 | 19 | 1368 | 0
T00299 | P019 | S03 | Nora Patel | Analytics | 2026-07-12 | 18 | 1476 | 18
T00300 | P019 | S04 | Owen Brooks | Development | 2026-07-18 | 19 | 1672 | 19
T00301 | P019 | S05 | Sara Lin | Project Management | 2026-05-21 | 16 | 1120 | 16
T00302 | P020 | S10 | Noah Reed | Strategy | 2026-06-07 | 17 | 1530 | 17
T00303 | P020 | S01 | Maya Chen | Strategy | 2026-06-24 | 19 | 1805 | 0
T00304 | P020 | S02 | Elias Ward | Design | 2026-06-27 | 16 | 1152 | 16
T00305 | P020 | S03 | Nora Patel | Analytics | 2026-06-19 | 11 | 902 | 11
T00306 | P020 | S04 | Owen Brooks | Development | 2026-05-24 | 20 | 1760 | 20
T00307 | P020 | S05 | Sara Lin | Project Management | 2026-06-25 | 21 | 1470 | 21
T00308 | P020 | S06 | Leo Martin | Development | 2026-06-11 | 21 | 1932 | 21
T00309 | P020 | S07 | Ava Stone | Content | 2026-05-23 | 12 | 696 | 12
T00310 | P020 | S08 | Theo King | Analytics | 2026-06-24 | 11 | 858 | 11
T00311 | P020 | S09 | Emma Hayes | Design | 2026-06-26 | 19 | 1292 | 19
T00312 | P020 | S10 | Noah Reed | Strategy | 2026-05-25 | 11 | 990 | 11
T00313 | P020 | S01 | Maya Chen | Strategy | 2026-05-18 | 19 | 1805 | 0
T00314 | P020 | S02 | Elias Ward | Design | 2026-05-16 | 14 | 1008 | 14
T00315 | P020 | S03 | Nora Patel | Analytics | 2026-06-21 | 19 | 1558 | 0
T00316 | P020 | S04 | Owen Brooks | Development | 2026-06-04 | 19 | 1672 | 19
T00317 | P020 | S05 | Sara Lin | Project Management | 2026-06-25 | 14 | 980 | 14
T00318 | P020 | S06 | Leo Martin | Development | 2026-06-12 | 11 | 1012 | 11
T00319 | P020 | S07 | Ava Stone | Content | 2026-06-15 | 19 | 1102 | 19
T00320 | P020 | S08 | Theo King | Analytics | 2026-06-12 | 14 | 1092 | 0
T00321 | P020 | S09 | Emma Hayes | Design | 2026-06-24 | 14 | 952 | 14
T00322 | P020 | S10 | Noah Reed | Strategy | 2026-06-02 | 15 | 1350 | 15
T00323 | P021 | S01 | Maya Chen | Strategy | 2026-07-06 | 39 | 3705 | 39
T00324 | P021 | S02 | Elias Ward | Design | 2026-06-26 | 36 | 2592 | 36
T00325 | P021 | S03 | Nora Patel | Analytics | 2026-07-04 | 21 | 1722 | 21
T00326 | P021 | S04 | Owen Brooks | Development | 2026-07-18 | 27 | 2376 | 27
T00327 | P021 | S05 | Sara Lin | Project Management | 2026-07-06 | 26 | 1820 | 0
T00328 | P021 | S06 | Leo Martin | Development | 2026-07-04 | 22 | 2024 | 22
T00329 | P021 | S07 | Ava Stone | Content | 2026-06-23 | 38 | 2204 | 0
T00330 | P021 | S08 | Theo King | Analytics | 2026-07-01 | 31 | 2418 | 31
T00331 | P021 | S09 | Emma Hayes | Design | 2026-07-19 | 39 | 2652 | 39
T00332 | P021 | S10 | Noah Reed | Strategy | 2026-07-19 | 25 | 2250 | 25
T00333 | P021 | S01 | Maya Chen | Strategy | 2026-06-16 | 26 | 2470 | 26
T00334 | P021 | S02 | Elias Ward | Design | 2026-06-11 | 32 | 2304 | 0
T00335 | P021 | S03 | Nora Patel | Analytics | 2026-07-17 | 27 | 2214 | 0
T00336 | P021 | S04 | Owen Brooks | Development | 2026-06-26 | 22 | 1936 | 22
T00337 | P021 | S05 | Sara Lin | Project Management | 2026-07-05 | 32 | 2240 | 32
T00338 | P021 | S06 | Leo Martin | Development | 2026-07-23 | 34 | 3128 | 34
T00339 | P021 | S07 | Ava Stone | Content | 2026-06-14 | 34 | 1972 | 34
T00340 | P021 | S08 | Theo King | Analytics | 2026-06-02 | 42 | 3276 | 42
T00341 | P021 | S09 | Emma Hayes | Design | 2026-07-27 | 35 | 2380 | 35
T00342 | P022 | S02 | Elias Ward | Design | 2026-08-31 | 33 | 2376 | 33
T00343 | P022 | S03 | Nora Patel | Analytics | 2026-06-22 | 33 | 2706 | 33
T00344 | P022 | S04 | Owen Brooks | Development | 2026-07-28 | 20 | 1760 | 20
T00345 | P022 | S05 | Sara Lin | Project Management | 2026-08-09 | 32 | 2240 | 32
T00346 | P022 | S06 | Leo Martin | Development | 2026-06-26 | 23 | 2116 | 23
T00347 | P022 | S07 | Ava Stone | Content | 2026-08-19 | 22 | 1276 | 22
T00348 | P022 | S08 | Theo King | Analytics | 2026-07-03 | 23 | 1794 | 23
T00349 | P022 | S09 | Emma Hayes | Design | 2026-08-14 | 34 | 2312 | 34
T00350 | P022 | S10 | Noah Reed | Strategy | 2026-07-02 | 20 | 1800 | 20
T00351 | P022 | S01 | Maya Chen | Strategy | 2026-07-04 | 29 | 2755 | 29
T00352 | P022 | S02 | Elias Ward | Design | 2026-06-19 | 19 | 1368 | 19
T00353 | P022 | S03 | Nora Patel | Analytics | 2026-08-28 | 27 | 2214 | 27
T00354 | P022 | S04 | Owen Brooks | Development | 2026-08-15 | 33 | 2904 | 33
T00355 | P022 | S05 | Sara Lin | Project Management | 2026-07-17 | 20 | 1400 | 20
T00356 | P022 | S06 | Leo Martin | Development | 2026-06-09 | 28 | 2576 | 28
T00357 | P022 | S07 | Ava Stone | Content | 2026-06-06 | 27 | 1566 | 27
T00358 | P022 | S08 | Theo King | Analytics | 2026-08-21 | 29 | 2262 | 29
T00359 | P022 | S09 | Emma Hayes | Design | 2026-08-17 | 21 | 1428 | 21
T00360 | P022 | S10 | Noah Reed | Strategy | 2026-06-17 | 25 | 2250 | 25
T00361 | P022 | S01 | Maya Chen | Strategy | 2026-07-02 | 24 | 2280 | 24
T00362 | P023 | S03 | Nora Patel | Analytics | 2026-07-15 | 26 | 2132 | 26
T00363 | P023 | S04 | Owen Brooks | Development | 2026-08-14 | 30 | 2640 | 30
T00364 | P023 | S05 | Sara Lin | Project Management | 2026-06-17 | 32 | 2240 | 32
T00365 | P023 | S06 | Leo Martin | Development | 2026-07-06 | 30 | 2760 | 30
T00366 | P023 | S07 | Ava Stone | Content | 2026-07-30 | 29 | 1682 | 29
T00367 | P023 | S08 | Theo King | Analytics | 2026-07-04 | 33 | 2574 | 33
T00368 | P023 | S09 | Emma Hayes | Design | 2026-08-13 | 27 | 1836 | 27
T00369 | P023 | S10 | Noah Reed | Strategy | 2026-07-06 | 22 | 1980 | 22
T00370 | P023 | S01 | Maya Chen | Strategy | 2026-07-07 | 33 | 3135 | 0
T00371 | P023 | S02 | Elias Ward | Design | 2026-07-25 | 20 | 1440 | 20
T00372 | P023 | S03 | Nora Patel | Analytics | 2026-06-11 | 32 | 2624 | 0
T00373 | P023 | S04 | Owen Brooks | Development | 2026-07-10 | 21 | 1848 | 21
T00374 | P023 | S05 | Sara Lin | Project Management | 2026-07-07 | 29 | 2030 | 29
T00375 | P023 | S06 | Leo Martin | Development | 2026-07-17 | 27 | 2484 | 27
T00376 | P023 | S07 | Ava Stone | Content | 2026-07-19 | 26 | 1508 | 0
T00377 | P023 | S08 | Theo King | Analytics | 2026-06-14 | 24 | 1872 | 24
T00378 | P023 | S09 | Emma Hayes | Design | 2026-08-26 | 26 | 1768 | 0
T00379 | P023 | S10 | Noah Reed | Strategy | 2026-08-07 | 9 | 810 | 9
T00380 | P024 | S04 | Owen Brooks | Development | 2026-08-31 | 10 | 880 | 10
T00381 | P024 | S05 | Sara Lin | Project Management | 2026-09-30 | 10 | 700 | 10
T00382 | P024 | S06 | Leo Martin | Development | 2026-09-08 | 8 | 736 | 0
T00383 | P024 | S07 | Ava Stone | Content | 2026-08-12 | 6 | 348 | 6
T00384 | P024 | S08 | Theo King | Analytics | 2026-07-13 | 8 | 624 | 8
T00385 | P024 | S09 | Emma Hayes | Design | 2026-08-04 | 12 | 816 | 12
T00386 | P024 | S10 | Noah Reed | Strategy | 2026-07-13 | 11 | 990 | 11
T00387 | P024 | S01 | Maya Chen | Strategy | 2026-07-05 | 7 | 665 | 0
T00388 | P024 | S02 | Elias Ward | Design | 2026-09-27 | 9 | 648 | 9
T00389 | P024 | S03 | Nora Patel | Analytics | 2026-08-17 | 7 | 574 | 7
T00390 | P024 | S04 | Owen Brooks | Development | 2026-08-10 | 12 | 1056 | 12
T00391 | P024 | S05 | Sara Lin | Project Management | 2026-07-01 | 6 | 420 | 6
T00392 | P024 | S06 | Leo Martin | Development | 2026-07-01 | 12 | 1104 | 12
T00393 | P024 | S07 | Ava Stone | Content | 2026-09-02 | 11 | 638 | 11
T00394 | P024 | S08 | Theo King | Analytics | 2026-08-02 | 9 | 702 | 9
T00395 | P024 | S09 | Emma Hayes | Design | 2026-08-28 | 11 | 748 | 11

## Vendor Costs
Vendor Costs
External delivery costs allocated to projects
Cost ID | Project ID | Cost Type | Date | Amount
V0001 | P001 | Production | 2026-01-21 | 916.59
V0002 | P001 | Freelance design | 2026-01-21 | 5921.63
V0003 | P002 | Freelance design | 2026-01-26 | 2990.88
V0004 | P003 | Research | 2026-01-31 | 1677.57
V0005 | P004 | Research | 2026-02-05 | 5150.2
V0006 | P004 | Hosting | 2026-02-05 | 2657.93
V0007 | P005 | Hosting | 2026-02-21 | 3130.29
V0008 | P006 | Production | 2026-02-26 | 1018.75
V0009 | P007 | Media spend | 2026-03-03 | 1158.98
V0010 | P007 | Research | 2026-03-03 | 2181.08
V0011 | P008 | Media spend | 2026-03-08 | 947.09
V0012 | P009 | Freelance design | 2026-03-21 | 2175.3
V0013 | P010 | Media spend | 2026-03-26 | 4943.88
V0014 | P010 | Hosting | 2026-03-26 | 4477.91
V0015 | P011 | Production | 2026-03-31 | 1438.09
V0016 | P012 | Research | 2026-04-05 | 5572.21
V0017 | P013 | Freelance design | 2026-04-21 | 4386.04
V0018 | P013 | Hosting | 2026-04-21 | 4564.09
V0019 | P014 | Hosting | 2026-04-26 | 3747.86
V0020 | P015 | Freelance design | 2026-05-01 | 5084.02
V0021 | P016 | Production | 2026-05-06 | 5813.22
V0022 | P016 | Hosting | 2026-05-06 | 5006.79
V0023 | P017 | Production | 2026-05-21 | 1097.69
V0024 | P018 | Production | 2026-05-26 | 2019.93
V0025 | P019 | Production | 2026-05-31 | 5491.17
V0026 | P019 | Freelance design | 2026-05-31 | 2772.31
V0027 | P020 | Research | 2026-06-05 | 4439.42
V0028 | P021 | Research | 2026-06-21 | 3834
V0029 | P022 | Media spend | 2026-06-26 | 5640.09
V0030 | P022 | Freelance design | 2026-06-26 | 2398.75
V0031 | P023 | Media spend | 2026-07-01 | 1434.42
V0032 | P024 | Production | 2026-07-06 | 2360.3

## Client Summary
Client Summary
Revenue, cost, profit and margin by account
Client | Industry | Projects | Revenue | Actual Cost | Gross Profit | Margin
Northstar Retail | Retail | 3 | 249800 | 123978.21 | 125821.79 | 50.37%
Lumen Health | Healthcare | 3 | 142100 | 73110.6 | 68989.4 | 48.55%
Atlas Property | Real Estate | 3 | 151100 | 86901.14 | 64198.86 | 42.49%
Orbit SaaS | Technology | 3 | 180600 | 98595.76 | 82004.24 | 45.41%
Cedar Finance | Financial Services | 3 | 166600 | 97755.42 | 68844.58 | 41.32%
BrightPath Learning | Education | 3 | 163500 | 93207.45 | 70292.55 | 42.99%
Harbor Legal | Legal | 3 | 201200 | 110949.5 | 90250.5 | 44.86%
PeakFit Clubs | Fitness | 3 | 176900 | 109230.4 | 67669.6 | 38.25%

## Checks
Checks & Controls
MODEL STATUS passes only when every reconciliation is within tolerance
Check | Expected | Actual | Delta | Status | Where to fix
Project count | 24 | 24 | 0 | PASS | Project Profitability
Revenue ties | 1431800 | 1431800 | 0 | PASS | Project Profitability
Labor cost ties | 687280 | 687280 | 0 | PASS | Time Entries
Vendor cost ties | 106448.48 | 106448.48 | -1.4552e-11 | PASS | Vendor Costs
Actual cost roll-up | 0 | 0 | 0 | PASS | Project Profitability
Profit equation | 0 | 1.1642e-10 | 1.1642e-10 | PASS | Project Profitability
Hours roll-up | 8738 | 8738 | 0 | PASS | Time Entries
Client revenue ties | 0 | 0 | 0 | PASS | Client Summary
Risk count ties | 5 | 5 | 0 | PASS | Dashboard
Missing project IDs | 0 | 0 | 0 | PASS | Project Profitability
MODEL STATUS | PASS
Passed Controls | 10 / 10